# DESIGN AND IMPLEMENTATION OF AN ONLINE HYPERMARKET COMMERCIAL CENTER

# Comprehensive 15-Day Implementation Plan — Free Tier Stack (Including Post-MVP Roadmap)

Final Year Engineering Project — 2026

# 1. PROJECT OVERVIEW AND SCOPE

This document provides the exhaustive, day-by-day implementation plan for building a working online hypermarket mobile application within 15 days. Every tool, service, and library used operates strictly on a free tier. By the end of Day 15, the application will be live, testable by real users, and ready for defense.

## 1.1 Core Features in the MVP

User Authentication: Register, login, logout with JWT. Roles: Customer, Vendor, Admin.

Product Catalog: Browse products by category (Groceries, Electronics, etc.). Search and filter.

Product Detail Page: Images, description, price, stock status, and customer reviews.

Shopping Cart: Persistent cart tied to user account.

Checkout and Payment: Stripe test-mode payment.

Order Tracking: Customer can view order status: Placed, Processing, Ready, Delivered.

Vendor Portal: Vendor can add products, update stock levels, and view incoming orders.

Push Notifications: Expo Push Notifications for order status updates.

# 2. TECHNOLOGY STACK — FREE TIER ONLY

| Layer | Technology | Free Tier Limits & Justification |
| --- | --- | --- |
| Frontend | React Native + Expo SDK 51 | Free forever. Cross-platform iOS/Android. |
| Backend | Node.js 20 + Express 4 | Lightweight, perfect for REST API. |
| Database | MongoDB Atlas (M0) | 512MB limit. Ideal for product document model. |
| Images | Cloudinary | 25GB storage. Auto-resize and CDN included. |
| Hosting | Render.com (Web Service) | 750 hours/month. Sleeps after 15min inactivity. |
| Payments | Stripe (Test Mode) | Free in test mode. Industry-standard SDK. |
| Distribution | Expo Go | Free testing without App Store submission. |

# 3. PROJECT FOLDER STRUCTURE

## 3.1 Backend Structure (Node.js)

hypermarket-backend/
├── src/
│   ├── config/ (db.js, cloudinary.js)
│   ├── middleware/ (auth.js, roleCheck.js)
│   ├── models/ (User.js, Product.js, Order.js, Cart.js, Category.js, Review.js)
│   ├── routes/ (auth, product, cart, order, vendor, payment, admin .routes.js)
│   ├── controllers/ (auth, product, cart, order, vendor, payment, admin .controller.js)
│   └── app.js (Express setup)
├── server.js (Entry point)
├── .env
└── package.json

## 3.2 Frontend Structure (React Native + Expo Router)

hypermarket-app/
├── app/
│   ├── (auth)/ (login.tsx, register.tsx)
│   ├── (customer)/ (index.tsx, category/[id].tsx, product/[id].tsx, cart.tsx, checkout.tsx, orders.tsx)
│   ├── (vendor)/ (dashboard.tsx, add-product.tsx, orders.tsx)
│   ├── (admin)/ (dashboard.tsx)
│   └── _layout.tsx
├── components/ (ProductCard, CategoryBar, CartItem, OrderStatusBadge, SearchBar)
├── store/ (authStore.ts, cartStore.ts - Zustand)
├── services/ (api.ts - Axios instance)
├── utils/ (responsive.ts)
└── app.json

# 4. DATABASE SCHEMA (MongoDB)

User Model: { _id, name, email, passwordHash, role: 'customer'|'vendor'|'admin', address: { street, city, country }, phone, expoPushToken, createdAt, updatedAt }

Product Model: { _id, name, description, price, comparePrice, category: ObjectId, vendor: ObjectId, images: [{ url, publicId }], stock: Number, unit, tags: [String], isPerishable: Boolean, averageRating, reviewCount, isActive: Boolean }

Order Model: { _id, customer: ObjectId, items: [{ product: ObjectId, name, price, quantity, vendorId }], totalAmount, status: 'placed'|'processing'|'ready'|'delivered', fulfilmentType: 'delivery'|'pickup', deliveryAddress, paymentIntentId, paymentStatus }

# 5. API CONTRACTS (Core Endpoints)

| Method & Endpoint | Auth Required | Description |
| --- | --- | --- |
| POST /api/auth/register | None | Register new user. Returns JWT. |
| POST /api/auth/login | None | Login user. Returns JWT. |
| GET /api/products | None | List products with search & filter params. |
| POST /api/products | Vendor | Create product. Multipart form for Cloudinary. |
| POST /api/cart/add | Customer | Add item to cart. Body: productId, quantity. |
| POST /api/orders | Customer | Place order from cart. Creates Stripe intent. |
| PUT /api/orders/:id/status | Vendor/Admin | Update order status. Triggers push notification. |
| POST /api/payment/create-intent | Customer | Create Stripe PaymentIntent. Returns clientSecret. |

# 6. EXHAUSTIVE 15-DAY IMPLEMENTATION PLAN

Each day assumes 6-8 focused working hours. Commit to GitHub at the end of every session.

## Phase 1: Backend Foundation (Days 1-5)

### Day 1: Project Setup + Auth API

- Run `npm init` and install `express mongoose dotenv bcryptjs jsonwebtoken cors multer cloudinary stripe`.

- Create free M0 cluster on MongoDB Atlas. Whitelist IP `0.0.0.0/0`.

- Write `src/config/db.js` and test MongoDB connection.

- Write `User.js` model with `bcrypt` pre-save hook.

- Build `auth.controller.js` (register/login) and `auth.middleware.js` (JWT verification). Test in Postman.

### Day 2: Product API + Cloudinary Integration

- Write `Category.js` and `Product.js` models. Add MongoDB text index on Product (`{name: 'text', description: 'text'}`).

- Configure `multer` for multipart parsing and `cloudinary.upload_stream` for image hosting.

- Build `POST /api/products` for vendors and `GET /api/products` (public) with query parsing (`?search=milk&category=123`).

### Day 3: Cart, Order, and Vendor API

- Write `Cart.js` model. Implement `addItem()` logic to check stock levels before incrementing quantity.

- Write `Order.js` model. Implement `placeOrder()`: validates cart, snapshots prices, clears cart, saves order.

- Build `GET /api/vendor/products` and `GET /api/vendor/orders` to restrict vendors to their own data.

### Day 4: Payment API + Push Notifications Backend

- Integrate Stripe: build `createPaymentIntent()` returning `clientSecret`.

- Set up Stripe Webhook `POST /api/payment/webhook` to update `Order.paymentStatus` to 'paid'.

- Build `POST /api/notifications/register` to save Expo push tokens. Integrate Expo SDK push trigger in the order status update controller.

### Day 5: Backend E2E Testing + Render.com Deployment

- Create a full Postman test suite covering the end-to-end flow.

- Push backend to GitHub and connect to Render.com Free Web Service.

- Configure all Production Environment Variables in Render.

- Add Render URL to Stripe Dashboard as the production webhook listener.

## Phase 2: Mobile App Frontend (Days 6-12)

### Day 6: Expo Setup + Zustand + Auth Screens

- Run `npx create-expo-app hypermarket-app`. Install `expo-router axios zustand @stripe/stripe-react-native`.

- Configure `axios` instance with request interceptor to inject JWT from `AsyncStorage`.

- Build Zustand `authStore` to manage global login state.

- Build `app/(auth)/login.tsx` and `register.tsx`. Set up role-based tab navigation rendering in `_layout.tsx`.

### Day 7: Home Screen & Catalog Navigation

- Build `Home` screen featuring a horizontal `CategoryBar` and `FeaturedProducts` FlatList.

- Create `ProductCard` component displaying Cloudinary image URLs and standardizing layout via responsive utilities.

- Build dynamic category screen (`app/(customer)/category/[id].tsx`) filtering via API query params.

### Day 8: Product Details, Reviews, and Cart State

- Build Product Details screen with image carousel and 'Add to Cart' functionality.

- Implement Zustand `cartStore` to sync local UI state with `PUT /api/cart` requests.

- Build `Cart` screen calculating subtotals and allowing quantity adjustments or item removal.

### Day 9: Checkout Flow & Stripe SDK

- Build Checkout screen with toggle for Home Delivery vs. BOPIS (Pickup).

- Wrap app layout in `StripeProvider`. Use Stripe `CardField` component.

- Implement flow: Call `/api/orders` -> Call `/api/payment/create-intent` -> Call Stripe `confirmPayment()`.

### Day 10: Customer Orders & Expo Push Handlers

- Build Customer Orders list view with color-coded `OrderStatusBadge` components.

- Request push notification permissions on app launch. Send token to backend via `/api/notifications/register`.

- Set up notification listener to refresh orders list when a push notification is received.

### Day 11: Vendor Portal & Product Uploads

- Build Vendor Dashboard showing active orders and revenue summaries.

- Build Add Product screen. Use `expo-image-picker` to select gallery images and transmit via `multipart/form-data`.

- Build Vendor Orders screen with dropdowns to update order status (triggering the customer push notifications).

### Day 12: Admin Dashboard & UI Polish

- Build basic Admin screen to list all users and all platform orders.

- Conduct a UI polish pass: ensure `ActivityIndicator` spinners are present during all Axios calls.

- Implement empty state illustrations (e.g., 'Your Cart is Empty').

## Phase 3: Integration, Testing and Launch (Days 13-15)

### Day 13: E2E Integration Testing

- Run complete Customer journey: Register -> Browse -> Cart -> Stripe Checkout (using 4242 test card) -> View Order.

- Run complete Vendor journey: Login -> Add Product -> Receive Order -> Update Status to 'Delivered'.

- Test edge cases: empty cart checkout blocks, expired token redirects to login, offline connection states.

### Day 14: Bug Fixes, Seed Data, and Expo Go Beta

- Write and execute a database seed script (`demo.js`) to generate 3 vendors, 20 products, and 10 sample orders to ensure the app looks fully populated for the defense.

- Run `npx expo publish` to generate a project QR code.

- Distribute the QR code to testers using Expo Go.

### Day 15: Final Documentation & Defense Prep

- Write the `README.md` detailing the tech stack, API endpoints, and local setup instructions.

- Prepare demo test accounts (Customer, Vendor, Admin credentials).

- Configure `cron-job.org` to ping the Render backend every 10 minutes to prevent cold starts during the project defense presentation.

# 7. PHASE 2 ROADMAP (Post-MVP)

The following features from the original project proposal are deliberately excluded from the 15-day MVP but will be implemented in Phase 2 to align the live product with the full architectural vision:

| Feature | Technology | Effort Estimate |
| --- | --- | --- |
| Replace MongoDB text search with Elasticsearch | Elastic Cloud Free Tier (14-day trial) or self-hosted | 3-5 days |
| Introduce Event-Driven Architecture | Replace direct REST calls with RabbitMQ (CloudAMQP free tier) or Kafka (Confluent Cloud free tier) | 5-7 days |
| Cold-chain IoT simulation | Simulate temperature sensor data with a Node.js cron job that randomly generates readings and alerts | 2-3 days |
| Vendor analytics dashboard | Recharts or Victory Native charts: revenue over time, best-selling products, order volume | 2-3 days |
| BOPIS collection bay QR confirmation | QR code generated per order, scanned by warehouse staff in vendor app to confirm pickup | 2-3 days |
| Full GDPR consent management | Add a consent screen on first launch, store consent timestamp, add data export and account deletion endpoints | 3-4 days |
| Product recommendation engine | Simple collaborative filtering using order history: customers who bought X also bought Y | 5-7 days |
| Multi-language support | i18n with expo-localization and i18next | 2-3 days |